## Sheet1
INFOSYS SPRINGBOARD INTERNSHIP - AGILE ENTERPRISE DATA CLEANING & ETL ORCHESTRATION FRAMEWORK USING PYTHON GROUP -7 TEAM MEMBERS : SHRINDHI, SHREYA, SHRUTI
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Setup project environment and folder structure | Must Have | None | Shreya | Done
Sprint 1 | Sprint 1 | US-002 | Create database tables using create_tables.py | Must Have | US-001 | Shrinidhi | Done
Sprint 1 | Sprint 1 | US-003 | Load CSV data into database using load_data.py | Must Have | US-002 | Sruthi | Done
Sprint 1 | Sprint 1 | US-004 | Validate data using check_data.py | Must Have | US-003 | Sruthi | Done (Verified)
Sprint 1 | Sprint 1 | US-005 | Capture outputs and screenshots | Should Have | US-004 | Shreya | Done
Sprint 1 | Sprint 1 | US-006 | Prepare documentation for milestone 1 | Should Have | US-005 | Shrinidhi | Done
Sprint 1 | Sprint 1 | US-007 | Update GitHub repository with milestone 1 work (weekly update) | Must Have | US-006 | Shreya, Shrinidhi | Done
Sprint 1 | Sprint 1 | US-006 | Prepare documentation for milestone 1 | Should Have | US-005 | Shrinidhi | Done
Sprint 2 | Sprint 2 | US-008 | Clean dataset by removing null values and duplicates | Must Have | US-004 | Shreya | Done
Sprint 2 | Sprint 2 | US-009 | Transform data by formatting dates and standardizing fields | Must Have | US-008 | Shrinidhi | Done
Sprint 2 | Sprint 2 | US-010 | Develop transform_data.py script for processing | Must Have | US-009 | Shrinidhi | Done
Sprint 2 | Sprint 2 | US-011 | Validate cleaned and transformed dataset | Should Have | US-010 | Shreya | Done (Tested)
Sprint 2 | Sprint 2 | US-012 | Capture outputs and screenshots | Should Have | US-011 | Shreya | Done
Sprint 2 | Sprint 2 | US-013 | Prepare documentation for milestone 2 | Should Have | US-012 | Shrinidhi | Done
Sprint 2 | Sprint 2 | US-014 | Update GitHub repository with milestone 2 work (weekly update) | Must Have | US-013 | Shreya, Shrinidhi | Done
Sprint 2 | Sprint 2 | US-013 | Prepare documentation for milestone 2 | Should Have | US-012 | Shrinidhi | Done
Sprint 3 | Sprint 3 | US-015 | Create Airflow DAG for ETL pipeline automation | Must Have | US-011 | Shreya | Done
Sprint 3 | Sprint 3 | US-016 | Schedule DAG execution at regular intervals (2 minutes) | Must Have | US-015 | Shreya | Done
Sprint 3 | Sprint 3 | US-017 | Implement logging in all ETL scripts (tracking enabled) | Must Have | US-015 | Shrinidhi | Done
Sprint 3 | Sprint 3 | US-018 | Configure email alerts in Airflow for failures | Should Have | US-016 | Shrinidhi | Done
Sprint 3 | Sprint 3 | US-019 | Test DAG execution in Airflow UI | Must Have | US-018 | Shreya, Shrinidhi | Done (Tested)
Sprint 3 | Sprint 3 | US-020 | Capture Airflow UI screenshots | Should Have | US-019 | Shreya | Done
Sprint 3 | Sprint 3 | US-021 | Prepare documentation for milestone 3 | Should Have | US-020 | Shrinidhi | Done
Sprint 3 | Sprint 3 | US-022 | Update GitHub repository with milestone 3 work (weekly update) | Must Have | US-021 | Shreya, Shrinidhi | Done
Sprint 3 | Sprint 3 | US-021 | Prepare documentation for milestone 3 | Should Have | US-020 | Shrinidhi | Done
Sprint 4 | Sprint 4 | US-023 | Design and create dashboard for data visualization | Must Have | US-019 | Shreya | Done
Sprint 4 | Sprint 4 | US-024 | Integrate database with dashboard and generate insights | Must Have | US-023 | Shrinidhi | Done
Sprint 4 | Sprint 4 | US-025 | Capture dashboard outputs and screenshots | Should Have | US-024 | Shreya | Done
Sprint 4 | Sprint 4 | US-026 | Update GitHub repository with final milestone work (weekly update) | Must Have | US-025 | Shreya, Shrinidhi | Done
Sprint 4 | Sprint 4 | US-027 | Prepare final documentation for milestone 4 | Must Have | US-026 | Shrinidhi | Done
Sprint 4 | Sprint 4 | US-028 | Prepare final presentation (PPT) with dashboard insights | Should Have | US-027 | Shreya | Done
Sprint 4 | Sprint 4 | US-029 | Perform final testing and validation of complete pipeline | Must Have | US-028 | Shreya, Shrinidhi | Done (Verified)
Sprint 4 | Sprint 4 | US-030 | Final project submission | Must Have | US-029 | Shreya, Shrinidhi | Done